## Slide 1: Plug-N-Harvest CCC Pilot Site
ORGANIZATION: ccc PRESENTER(S): Gareth Harcombe MEETING: CCC Pilot Site: February 2019, Aachen

## Slide 2: Work done/being done
WP1 – contributed to all requirements.
Commissioned Revit (interrogatable files) of the CCC pilot and a structural survey completed by consultants.
Working with WP1 & WP3 lead to procure & install sensors to meet project KPIs.
WP2/4 – contributing to meetings to integrate ADBE concept design with pilot site requirements and introduction of potential new project partner.
WP4 – see next slide
WP5 – contribution to T5.1 Circular Economy Design & T5.3 Life Cycle Costing
WP6 – contribution to T6.1 Dissemination and Data Mgt Plans & T6.2 Dissemination Channels
WP7 – contribution to T7.1 Project Co-ordination and Financial Management & T7.2 Quality Assurance

## Slide 3: WP4 Progress
Sensors/Meters
80% of sensors/meters agreed with WP3 lead. Still to agree solar radiation sensor and suitable sensor for hot water use. CCC IT dept to progress installation on site.
No ‘window contact sensors’.
Support from Odins for onsite installation?
Site installation anticipated April 2019.
No progress with ADBE actuators/sensors. Selection and design of ADBE components not yet determined.

## Slide 5: Day 2 – work to do & points to address
To do:
Tenants to sign ‘consent form’. All agreed in principle. Formal signature in progress (March 2019).
Order sensors for project KPIs and install (March – April 2019).
Points to address:
Design – integration of conventional façade (CF) with ADBE modules (see module type configuration previous slide).
Assurance of ADBE modules (not individual elements) to be acceptable to UK regulations and CCC insurance. TRL level 7 guarantee.
Budget amendment confirmation (submitted March 2018).

## Slide 6
THANK YOU
PLUG-N-HARVEST ID: 768735 - H2020-EU.2.1.5.2.