## Slide 1: Plug-N-Harvest
WP 6-7 : Dissemination, Communication & project Management activities
ORGANIZATION: CERTH PRESENTER(S): christos ravanis MEETING: 3Rd plenary, BARCELONA, 06-08 juNE 2018

## Slide 2: Mail lists – Publications
PnH Google group replaced by ITI’s mail list (Jan 2018)
External stakeholder’s survey
Publication in the EeB PPP Project Review 2018
Other??????

## Slide 3: Telcos
WP1 initial: October 11 coordination: November 9 and 23, December 13, January 4, April 17 (KPI coordination)
WP3 initial: January 8 coordination: January 18
WP5 initial: December 13 coordination: January 4, April 10 (task 5.6 webinar)

## Slide 4: In person Meetings
When | Who | Purpose
May 17, 2018 | ALUMIL, RWM | Greek pilot definition

## Slide 5: Deliverables
Already delivered (scheduled for M4)
Del. No | Title | Responsible | version
D6.1 | Dissemination Plans and Promotion | CERTH | 1st version [D6.1.1 a]
D6.2 | Data Management Plan | CERTH | 1st version [D6.1.2 a]
D7.1 | Project Management | CERTH | [D7.1.1]
D7.4 | Quality Assessment Plan | CERTH | [D7.2.1]
D7.5 | Risk Assessment | CERTH | [D7.2.2]
D7.6 | Ethical Monitoring and Contingency plans | CERTH | [D7.2.3]

## Slide 6: Deliverables
To be delivered until end of August 2018 (M12)
Del. No | Title | Responsible | version
D1.1 | End-Users and Business Requirements Report | AIGUASOL | 1st version [D1.1 a]
D1.2 | Use Case Site Survey and Audit Report | CU | 1st version [D1.2.1 a]
D1.3 | Evaluation Plan | CU | 1st version [D1.2.2 a]
D1.4 | Systems engineering requirements definition | CU | 1st version [D1.3 a]
D5.7 | Report On Standardization Models | ALUMIL | 1st version [D5.5 a]
D5.8 | Market Analysis & Business Plans | AIGUASOL | 1st version [D5.6.1 a]
D5.9 | Exploitation Plans | AIGUASOL | 1st version [D5.6.2 a]
D6.4 | Dissemination Activities Annual Report | CERTH | 1st version [D6.2.2 a]
D7.2 | Progress Periodic Management Reports | CERTH | 1st version [D7.1.2 a]

## Slide 7: Open issues
Move part of the budget (~20%) from pilot partners (RWTH, AHC, RWM, CCC) to ALUMIL for
  Mould
  Profiles
  Assembly materials
Move part of the budget (about €3,000) from pilot partners (RWTH, AHC, RWM, CCC) to ODINS for data routing equipment
Pilot’s revised budget finalization, including
  facade's construction
  transport and installation costs
  subcontracting processes
4th Plenary meeting / 1st Review meeting dates